## Detail
COST CALCULATION FOR GIS CONSULTING PROJECT
|  | Labor Hours and Cost for Team Members | [7 empty] | Direct Expenses
| Person: | PC | MR | TL | xx | cler |  |  | Cost Item: | Lodging | Car Miles | Airfare | Meals | Parking | Rent Car | Refreshments | Other
| Rate: | 125 | 100 | 60 | 0 | 20 | TOTAL LABOR |  | Unit: | 1 night | 1 mile | roundtrip | 1 day | 1 day | 1 day | day |  | TOTAL
Task Number and Name | Multiplier: | 1 | 1 | 1.2 | 1 | 1.1 | Hours | Cost | Cost: | 95 | 0.45 | 350 | 40 | 9 | 50 | 70 | 50 | EXPENSES | GRAND TOTAL
Task 1: Project Start-up and Planning
1.1 Review Background Documents |  | 5 | 5 | 4 |  |  | 14 | 1413 | [9 empty] | 0 | 1413
1.2 Prepare Detailed Schedule (draft) |  | 2 | 2 |  |  |  | 4 | 450 | [9 empty] | 0 | 450
1.3 Organize/Conduct Kick-off Meeting |  | 11 | 8 |  |  |  | 19 | 2175 |  | 2 | 450 | 1 | 2 | 1 |  |  | 4 | 1031.5 | 3206.5
1.4 Final Schedule/Proj. Mngmnt Guide |  | 3 | 1 |  |  |  | 4 | 475 | [9 empty] | 0 | 475
PROJECT MANAGEMENT |  | 4 | 1 | 1 |  |  | 6 | 672 | [9 empty] | 0 | 672
Sub-total: |  | 25 | 17 | 5 | 0 | 0 | 47 | 5185 | # of Units: | 2 | 450 | 1 | 2 | 1 | 0 | 0 | 4 | 1031.5 | 6216.5
[9 empty] | Cost: | 190 | 202.5 | 350 | 80 | 9 | 0 | 0 | 200 | 1031.5
Task 2: Design, Deploy Web-based Survey
2.1 Design and Create Prototype |  | 2 | 20 | 2 |  |  | 24 | 2394 | [9 empty] | 0 | 2394
2.2 Test/Deploy Final Tool |  | 2 | 10 |  |  |  | 12 | 1250 | [9 empty] | 0 | 1250
2.3 Encourage Survey Responses |  | 2 | 3 |  |  |  | 5 | 550 | [9 empty] | 0 | 550
2.4 Monitor/Support Survey |  | 1 | 8 |  |  |  | 9 | 925 | [9 empty] | 0 | 925
PROJECT MANAGEMENT |  | 3 | 2 |  |  |  | 5 | 575 | [9 empty] | 0 | 575
Sub-total: |  | 10 | 43 | 2 | 0 | 0 | 55 | 5694 | # of Units: | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5694
[9 empty] | Cost: | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task 3: Regional Forums and Interviews
3.1 Organize/Prepare for Regional Forums |  | 12 | 6 | 3 |  | 4 | 25 | 2404 | [9 empty] | 0 | 2404
3.2 Conduct Regional Forums |  | 40 | 20 | 2 |  |  | 62 | 7144 |  | 6 | 2200 | 1 | 8 | 1 |  |  |  | 2239 | 9383
3.3 Organize and Conduct Interviews |  | 40 | 5 |  |  |  | 45 | 5500 |  | 1 | 400 |  | 2 |  |  | 5 |  | 705 | 6205
3.4 Follow-up as needed |  | 20 | 8 | 3 |  |  | 31 | 3516 | [9 empty] | 0 | 3516
3.5 Gather info from other states |  | 3 | 8 | 4 |  |  | 15 | 1463
PROJECT MANAGEMENT |  | 3 | 2 | 1 |  |  | 6 | 647 | [9 empty] | 0 | 647
Sub-total: |  | 118 | 49 | 13 | 0 | 4 | 184 | 20674 | # of Units: | 7 | 2600 | 1 | 10 | 1 | 0 | 5 | 0 | 2944 | 23618
[9 empty] | Cost: | 665 | 1170 | 350 | 400 | 9 | 0 | 350 | 0 | 2944
Task 4: Evaluate/Document Info Gathering
4.1 Compile Survey Results |  | 3 | 24 | 3 |  | 12 | 42 | 3255 | [9 empty] | 0 | 3255
4.2 Summarize Regional Forums |  | 18 | 12 | 2 |  | 5 | 37 | 3704 | [9 empty] | 0 | 3704
4.3 Summarize Interviews |  | 20 | 5 | 2 |  | 1 | 28 | 3166 | [9 empty] | 0 | 3166
4.4 Distribute and Review Summaries |  | 4 | 4 | 1 |  | 1 | 10 | 994 | [9 empty] | 0 | 994
PROJECT MANAGEMENT |  | 3 | 3 | 1 |  |  | 7 | 747 | [9 empty] | 0 | 747
Sub-total: |  | 48 | 48 | 9 | 0 | 19 | 124 | 11866 | # of Units: | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11866
[9 empty] | Cost: | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task 5: Develop Draft Business Plan
5.1 Prepare and Approve Outline |  | 2 |  |  |  |  | 2 | 250 | [9 empty] | 0 | 250
5.2 Prepare Draft Section on Funding |  | 6 | 5 | 5 |  | 3 | 19 | 1676 | [9 empty] | 0 | 1676
5.3 Review/Comment on Draft Section |  | 2 |  |  |  |  | 2 | 250 | [9 empty] | 0 | 250
5.4 Prepare/Submit Full 1st Draft |  | 28 | 20 | 5 |  | 8 | 61 | 6036 | [9 empty] | 0 | 6036
5.5 Review/Comment on 1st Draft |  | 12 | 12 | 2 |  |  | 26 | 2844 |  | 2 | 420 | 1 | 2 |  |  |  |  | 809 | 3653
5.6 Prepare/Submit 2nd Draft |  | 12 | 12 | 5 |  | 8 | 37 | 3236 | [9 empty] | 0 | 3236
5.7 Review/Comment on 2nd Draft |  | 3 | 1 |  |  |  | 4 | 475 | [9 empty] | 0 | 475
5.8 Mid-TN GIS Forum Presentation |  | 8 |  |  |  |  | 8 | 1000 |  |  | 420 |  | 1 |  |  |  | 1 | 279 | 1279
PROJECT MANAGEMENT |  | 3 | 3 |  |  |  | 6 | 675 | [9 empty] | 0 | 675
Sub-total: |  | 76 | 53 | 17 | 0 | 19 | 165 | 16442 | # of Units: | 2 | 840 | 1 | 3 | 0 | 0 | 0 | 1 | 1088 | 17530
[9 empty] | Cost: | 190 | 378 | 350 | 120 | 0 | 0 | 0 | 50 | 1088
Task 6: Final Business Plan/Exec. Summary
6.1 Prepare/Submit Final Draft |  | 10 | 5 | 2 |  | 8 | 25 | 2070 | [9 empty] | 0 | 2070
6.2 Review/Comment on Final Draft |  | 3 | 2 | 2 |  |  | 7 | 719 | [9 empty] | 0 | 719
6.3 Prepare/Submit Final Business Plan |  | 6 |  |  |  | 4 | 10 | 838 | [9 empty] | 0 | 838
6.4 Prepare Draft Exec Summary Materials |  | 6 | 6 |  |  | 2 | 14 | 1394 | [9 empty] | 0 | 1394
6.5 Review/Comment on Draft Materials |  | 2 |  |  |  |  | 2 | 250 | [9 empty] | 0 | 250
6.6 Prepare/Conduct Exec. Presentation |  | 8 |  |  |  | 2 | 10 | 1044 |  | 1 | 420 |  | 2 |  |  |  |  | 364 | 1408
6.7 Prepare MSProject File |  | 6 |  | 2 |  |  | 8 | 894 | [9 empty] | 0 | 894
PROJECT MANAGEMENT |  | 4 | 2 |  |  |  | 6 | 700 | [9 empty] | 0 | 700
Sub-total: |  | 45 | 15 | 6 | 0 | 16 | 82 | 7909 | # of Units: | 1 | 420 | 0 | 2 | 0 | 0 | 0 | 0 | 364 | 8273
[9 empty] | Cost: | 95 | 189 | 0 | 80 | 0 | 0 | 0 | 0 | 364
Task 7: Prepare LiDAR Specifications
7.1 Review Draft/Research Other Organizations |  | 4 | 8 | 3 |  |  | 15 | 1516 | [9 empty] | 0 | 1516
7.1 Recommendations/Review with Working Group |  | 11 | 2 | 1 |  |  | 14 | 1647 |  | 2 | 420 |  | 3 |  |  |  |  | 499 | 2146
7.3 Prepare/Submit Revised LiDAR Specs |  | 8 | 16 | 8 |  | 6 | 38 | 3308 | [9 empty] | 0 | 3308
7.4 Final Revised LiDAR Specifications |  | 2 | 8 | 3 |  | 4 | 17 | 1354 | [9 empty] | 0 | 1354
PROJECT MANAGEMENT |  | 2 | 2 |  |  |  | 4 | 450 | [9 empty] | 0 | 450
Sub-total: |  | 27 | 36 | 15 | 0 | 10 | 88 | 8275 | # of Units: | 2 | 420 | 0 | 3 | 0 | 0 | 0 | 0 | 499 | 8774
[9 empty] | Cost: | 190 | 189 | 0 | 120 | 0 | 0 | 0 | 0 | 499
Task 8: Project Closure and BP Submittal to FGDC
8.1 Prepare Final Project Status Report |  | 2 | 1 |  |  |  | 3 | 350 | [9 empty] | 0 | 350
8.2 Submittal of Business Plan to FGDC |  | 1 | 1 |  |  |  | 2 | 225 | [9 empty] | 0 | 225
PROJECT MANAGEMENT | [6 empty] | 0 | 0 |  |  | 420 |  | 1 |  |  |  |  | 229 | 229
Sub-total: |  | 3 | 2 | 0 | 0 | 0 | 5 | 575 | # of Units: | 0 | 420 | 0 | 1 | 0 | 0 | 0 | 0 | 229 | 804
[9 empty] | Cost: | 0 | 189 | 0 | 40 | 0 | 0 | 0 | 0 | 229
GRAND TOTAL: |  | 352 | 263 | 67 | 0 | 68 | 750 | 76620 | # of Units: | 14 | 5150 | 3 | 21 | 2 | 0 | 5 | 5 | 6155.5 | 82775.5
[9 empty] | Cost: | 1330 | 2317.5 | 1050 | 840 | 18 | 0 | 350 | 250 | 6155.5

## SUMMARY
COST CALCULATION FOR CARLSBAD PROPOSAL
Projected Labor Hours and Cost | [7 empty] | Direct Expenses
Person: | PC | MR | TL | xx | cler | TOTAL
Rate: | 125 | 100 | 60 | 0 | 20 | Hours | Cost | Lodging | Transport. | Meals | Other | TOTAL EXPENSES | GRAND TOTAL
Task 1: Project Start-up and Planning
| 25 | 17 |  | 5 | 0 | 47 | 5185 | 190 | 561.5 | 80 | 200 | 1031.5 | 6216.5
Task 2: Design, Deploy Web-based Survey
| 10 | 43 |  | 2 | 0 | 55 | 5694 | 0 | 0 | 0 | 0 | 0 | 5694
Task 3: Regional Forums and Interviews
| 118 | 49 |  | 13 | 4 | 184 | 20674 | 665 | 1529 | 400 | 350 | 2944 | 23618
Task 4: Evaluate/Document Info Gathering
| 48 | 48 |  | 9 | 19 | 124 | 11866 | 0 | 0 | 0 | 0 | 0 | 11866
Task 5: Develop Draft Business Plan
| 76 | 53 |  | 17 | 19 | 165 | 16442 | 190 | 728 | 120 | 50 | 1088 | 17530
Task 6: Final Business Plan/Exec. Summary
| 45 | 15 |  | 6 | 16 | 82 | 7909 | 95 | 189 | 80 | 0 | 364 | 8273
Task 7: Prepare LiDAR Specifications
| 27 | 36 | 15 | 0 | 10 | 88 | 894 | 190 | 189 | 120 | 0 | 499 | 8774
Task 8: Project Closure and BP Submittal to FGDC
| 3 | 2 | 0 | 0 | 0 | 5 | 8275 | 0 | 189 | 40 | 0 | 229 | 804
GRAND TOTAL: | 352 | 263 |  | 67 | 68 | 750 | 76620 | 1330 | 3385.5 | 840 | 600 | 6155.5 | 82775.5
[13 empty] | Check total: | 82775.5

## Sheet3
5190 | 0 | 0 | 0 | 5190
10739 | 764 | 665 | 280 | 12448
8660 | 0 | 0 | 0 | 8660
5789 | 0 | 0 | 0 | 5789
6696 | 487 | 190 | 100 | 7473
7178 | 0 | 0 | 0 | 7178
2620 | 478 | 95 | 80 | 3273
3268 | 0 | 0 | 0 | 3268
50140 | 1729 | 950 | 460 | 53279